## Executive_Dashboard
North Sea Oil Platform Drill Tower Construction - Executive EVM Outturn Report
Metric Name | Value ($ / %) | Status / Notes
Total Baseline Budget (BAC) | 26500000 | Approved Scope Anchor
Cumulative Planned Value (PV) | 20500000 | BCWS Baseline Plan (Month 8)
Cumulative Earned Value (EV) | 17540000 | BCWP Physical Progress (60.8%)
Cumulative Actual Cost (AC) | 23440000 | ACWP Ledger Spend Incurred
Cost Variance (CV = EV - AC) | -5900000 | Critical Overrun
Schedule Variance (SV = EV - PV) | -2960000 | Schedule Slippage
Cost Performance Index (CPI) | 0.7483 | Critical Cost Efficiency Deficit
Schedule Performance Index (SPI) | 0.8556 | Schedule Execution Delay
Critical Ratio (CR = CPI * SPI) | 0.6402 | Critical Combined Deficit
Outturn Forecast (EAC = BAC / CPI) | 35413604 | Projected Final Outturn
Variance at Completion (VAC = BAC - EAC) | -8913604 | Projected Final Deficit
Earned Schedule (ES) | 7.4 | Lipke Time-Based Progress
Time-Based Index SPI(t) | 0.925 | Time Variance: -18 Days
Control Account EVM Performance Matrix (Month 8 Status Date)
Task_ID | WBS_Code | Task_Name | CAM | BAC ($)
T101 | 1.1.1 | Structural Steel Detail Engineering | H. Lindqvist | 1200000
T102 | 1.1.2 | Piping & Drilling Package Design | H. Lindqvist | 1800000
T103 | 1.2.1 | High-Grade Tubular Steel Procurement | M. Berg | 3500000
T104 | 1.2.2 | Mud Pumps & Top Drive Equipment | M. Berg | 4200000
T105 | 1.3.1 | Yard Sub-Structure Fabrication (Verdal) | O. Eriksen | 4000000
T106 | 1.3.2 | Derrick Tower Mast Assembly (Egersund) | O. Eriksen | 4800000
T107 | 1.4.1 | Heavy Lift Vessel Mobilization (Heerema) | K. Solberg | 2500000
T108 | 1.4.2 | Offshore Topside Lifting & Mating | K. Solberg | 2000000
T109 | 1.5.1 | Structural Hook-up & NDT Inspection | T. Nygård | 1000000
T110 | 1.5.2 | System Pre-Commissioning & Handover | T. Nygård | 1500000
Total |  | Total Portfolio Scope

## PV_Baseline
Item_ID | WBS_Code | Task_Name | TBC | Month_1 | Month_2 | Month_3 | Month_4 | Month_5 | Month_6 | Month_7 | Month_8 | Month_9 | Month_10 | Month_11 | Month_12
T101 | 1.1.1 | Structural Steel Detail Engineering | 1200000 | 300000 | 500000 | 400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T102 | 1.1.2 | Piping & Drilling Package Design | 1800000 | 0 | 400000 | 800000 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T103 | 1.2.1 | High-Grade Tubular Steel Procurement | 3500000 | 0 | 0 | 1000000 | 2000000 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T104 | 1.2.2 | Mud Pumps & Top Drive Equipment | 4200000 | 0 | 0 | 500000 | 1200000 | 1500000 | 1000000 | 0 | 0 | 0 | 0 | 0 | 0
T105 | 1.3.1 | Yard Sub-Structure Fabrication (Verdal) | 4000000 | 0 | 0 | 0 | 0 | 1000000 | 2000000 | 1000000 | 0 | 0 | 0 | 0 | 0
T106 | 1.3.2 | Derrick Tower Mast Assembly (Egersund) | 4800000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 2000000 | 1800000 | 0 | 0 | 0 | 0
T107 | 1.4.1 | Heavy Lift Vessel Mobilization (Heerema) | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1500000 | 0 | 0 | 0
T108 | 1.4.2 | Offshore Topside Lifting & Mating | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000 | 1000000 | 0 | 0
T109 | 1.5.1 | Structural Hook-up & NDT Inspection | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 0
T110 | 1.5.2 | System Pre-Commissioning & Handover | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000

## EV_Progress
Item_ID | WBS_Code | Task_Name | TBC | Month_1_% | Month_2_% | Month_3_% | Month_4_% | Month_5_% | Month_6_% | Month_7_% | Month_8_% | Month_9_% | Month_10_% | Month_11_% | Month_12_%
T101 | 1.1.1 | Structural Steel Detail Engineering | 1200000 | 25% | 65% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T102 | 1.1.2 | Piping & Drilling Package Design | 1800000 | 0% | 20% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T103 | 1.2.1 | High-Grade Tubular Steel Procurement | 3500000 | 0% | 0% | 20% | 70% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
T104 | 1.2.2 | Mud Pumps & Top Drive Equipment | 4200000 | 0% | 0% | 10% | 35% | 60% | 75% | 85% | 85% | 85% | 85% | 85% | 85%
T105 | 1.3.1 | Yard Sub-Structure Fabrication (Verdal) | 4000000 | 0% | 0% | 0% | 0% | 20% | 55% | 80% | 90% | 90% | 90% | 90% | 90%
T106 | 1.3.2 | Derrick Tower Mast Assembly (Egersund) | 4800000 | 0% | 0% | 0% | 0% | 0% | 15% | 40% | 65% | 65% | 65% | 65% | 65%
T107 | 1.4.1 | Heavy Lift Vessel Mobilization (Heerema) | 2500000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 30% | 30% | 30% | 30%
T108 | 1.4.2 | Offshore Topside Lifting & Mating | 2000000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
T109 | 1.5.1 | Structural Hook-up & NDT Inspection | 1000000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
T110 | 1.5.2 | System Pre-Commissioning & Handover | 1500000 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## AC_Actuals
Item_ID | WBS_Code | Task_Name | TBC | Month_1_AC | Month_2_AC | Month_3_AC | Month_4_AC | Month_5_AC | Month_6_AC | Month_7_AC | Month_8_AC | Month_9_AC | Month_10_AC | Month_11_AC | Month_12_AC
T101 | 1.1.1 | Structural Steel Detail Engineering | 1200000 | 320000 | 540000 | 430000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T102 | 1.1.2 | Piping & Drilling Package Design | 1800000 | 0 | 410000 | 850000 | 620000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T103 | 1.2.1 | High-Grade Tubular Steel Procurement | 3500000 | 0 | 0 | 1100000 | 2150000 | 520000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T104 | 1.2.2 | Mud Pumps & Top Drive Equipment | 4200000 | 0 | 0 | 520000 | 1280000 | 1600000 | 1100000 | 450000 | 0 | 0 | 0 | 0 | 0
T105 | 1.3.1 | Yard Sub-Structure Fabrication (Verdal) | 4000000 | 0 | 0 | 0 | 0 | 1100000 | 2200000 | 1150000 | 450000 | 0 | 0 | 0 | 0
T106 | 1.3.2 | Derrick Tower Mast Assembly (Egersund) | 4800000 | 0 | 0 | 0 | 0 | 0 | 1150000 | 2250000 | 2050000 | 0 | 0 | 0 | 0
T107 | 1.4.1 | Heavy Lift Vessel Mobilization (Heerema) | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200000 | 0 | 0 | 0 | 0
T108 | 1.4.2 | Offshore Topside Lifting & Mating | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T109 | 1.5.1 | Structural Hook-up & NDT Inspection | 1000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T110 | 1.5.2 | System Pre-Commissioning & Handover | 1500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Gantt_Schedule
Task_ID | Task_Name | WBS_Code | CAM | Baseline_Start | Baseline_End | Actual_Start | Actual_End | Predecessor_Task_ID | Predecessor_Name | Dependency_Type | Lag_Days | Percent_Complete | Critical_Path_Flag | Resource_Group
T101 | Structural Steel Detail Engineering | 1.1.1 | H. Lindqvist | 2026-01-05 | 2026-02-28 | 2026-01-05 | 2026-03-15 |  |  |  | 0 | 1 | Yes | Engineering Team
T102 | Piping & Drilling Package Design | 1.1.2 | H. Lindqvist | 2026-02-01 | 2026-03-31 | 2026-02-01 | 2026-04-15 | T101 | Structural Steel Detail Engineering | FS | 0 | 1 | No | Engineering Team
T103 | High-Grade Tubular Steel Procurement | 1.2.1 | M. Berg | 2026-03-01 | 2026-04-30 | 2026-03-15 | 2026-05-31 | T101 | Structural Steel Detail Engineering | FS | 5 | 1 | Yes | Procurement Team
T104 | Mud Pumps & Top Drive Equipment | 1.2.2 | M. Berg | 2026-03-15 | 2026-06-30 | 2026-04-01 | 2026-07-31 | T102 | Piping & Drilling Package Design | FS | 0 | 0.85 | No | Procurement Team
T105 | Yard Sub-Structure Fabrication (Verdal) | 1.3.1 | O. Eriksen | 2026-05-01 | 2026-07-31 | 2026-06-01 | 2026-08-31 | T103 | High-Grade Tubular Steel Procurement | FS | 0 | 0.9 | Yes | Verdal Fabrication Yard
T106 | Derrick Tower Mast Assembly (Egersund) | 1.3.2 | O. Eriksen | 2026-06-01 | 2026-08-31 | 2026-07-01 | 2026-09-30 | T105 | Yard Sub-Structure Fabrication (Verdal) | FS | 0 | 0.65 | Yes | Egersund Rigging Yard
T107 | Heavy Lift Vessel Mobilization (Heerema) | 1.4.1 | K. Solberg | 2026-08-15 | 2026-09-15 | 2026-09-15 | 2026-10-15 | T106 | Derrick Tower Mast Assembly (Egersund) | FS | 0 | 0.3 | Yes | Offshore Marine Fleet
T108 | Offshore Topside Lifting & Mating | 1.4.2 | K. Solberg | 2026-09-15 | 2026-10-15 | 2026-10-15 | 2026-11-15 | T107 | Heavy Lift Vessel Mobilization (Heerema) | FS | 0 | 0 | Yes | Offshore Marine Fleet
T109 | Structural Hook-up & NDT Inspection | 1.5.1 | T. Nygård | 2026-10-15 | 2026-11-15 | 2026-11-15 | 2026-12-15 | T108 | Offshore Topside Lifting & Mating | FS | 0 | 0 | Yes | Offshore Hook-Up Crew
T110 | System Pre-Commissioning & Handover | 1.5.2 | T. Nygård | 2026-11-15 | 2026-12-31 | 2026-12-15 | 2027-01-31 | T109 | Structural Hook-up & NDT Inspection | FS | 0 | 0 | Yes | Commissioning Team