## Slide 1
North Sea Oil Platform Drill Tower Construction
Integrated Earned Value Management (EVM), Schedule Control & Risk Briefing
Status Date: August 31, 2026 (Month 8 / Week 36) | Prepared By: Frank Ellingsen, Lead Project Controller

## Slide 2
1. Executive Steering Committee Status Briefing
Overall Project Health: 🚨 CRITICAL COST OVERRUN & SCHEDULE SLIPPAGE (RED)
🚨 OVERALL HEALTH: CRITICAL (RED) | BAC Budget Burn Out: Month 9 (Sep 2026) | Required Financing: +$8.91M
BASELINE BUDGET (BAC)
$26.50M
Approved baseline target
EARNED VALUE (EV)
$17.54M
66.2% Work Complete
ACTUAL SPEND (AC)
$23.44M
Spent to date
COST INDEX (CPI)
0.75
Severe overrun ($0.75/$1)
TIME INDEX (SPIT)
0.925
-18.2 Days Schedule Slip
Scenario | EAC Outturn | Completion Date
Deterministic Base | $35,413,604 | Jan 31, 2027 (+31d)
Monte Carlo P50 | $34,060,783 | Feb 27, 2027 (+57d)
Monte Carlo P90 | $35,815,202 | Mar 14, 2027 (+72d)
REQUIRED STEERING COMMITTEE ACTIONS
1. Authorize Overrun Credit Line: Secure +$8.91M financing before September 15, 2026 (Month 9 budget exhaustion).
2. Cap Yard Rework Billing: Transition Egersund yard (WBS 1.3.2) to a fixed-fee labor cap for remaining mast assembly.
3. Compress Offshore Hook-up: Recover 15 calendar days to preserve January 31, 2027 Commercial COD.
4. Enforce Change Freeze: Freeze all pending baseline scope change requests across WBS 1.3 deliverables.

## Slide 3
2. Monthly Cash Burn Speed & Budget Depletion Forecast
Exact BAC Budget Exhaustion Point: Month 9 (September 2026)
AVG MONTHLY CASH BURN
$2.93M / Mo
Baseline Plan: $2.56M/Mo (+14.5%)
REMAINING CAPITAL ($BAC-AC)
$3.06M
$23.44M spent of $26.50M BAC
BUDGET BURN OUT MONTH
Month 9 (Sep 2026)
100% of BAC budget exhausted
REQUIRED OVERRUN FINANCING
+$8,913,604
Must be approved before Sep 15
Month | Planned Monthly ($PV) | Earned Monthly ($EV) | Actual Monthly ($AC) | Budget Status & Runway Note
Month 1 (Jan) | $0.30M | $0.30M | $0.32M | Engineering ramp-up
Month 2 (Feb) | $0.90M | $0.84M | $0.95M | Detail steel design completed
Month 3 (Mar) | $2.70M | $2.26M | $2.90M | Procurement placement delays
Month 4 (Apr) | $3.80M | $3.52M | $4.05M | Verdal yard fabrication start
Month 5 (May) | $3.00M | $2.90M | $3.22M | Sub-structure assembly
Month 6 (Jun) | $4.00M | $2.75M | $4.45M | Egersund mast dimensional fitting rework
Month 7 (Jul) | $3.00M | $2.62M | $3.85M | Double-shift NDT welding hours
Month 8 (Aug) | $2.80M | $2.35M | $3.70M | Status Date: $23.44M cumulative spend
Month 9 (Sep) | $2.50M (FC) | $2.10M (FC) | $3.20M (FC) | 💥 100% BAC Budget Exhausted (Sep 2026)

## Slide 4
3. Cost Variance Waterfall Bridge ($BAC → EAC Outturn)
Step-by-Step Cost Variance Drivers from Baseline to Outturn Forecast
WBS / Step Description | Variance Amount | Impact Category | Driver & Root Cause Analysis
Approved Baseline Budget ($BAC) | $26.50M | Baseline | Original contract baseline target
WBS 1.1 Engineering | +$0.30M | Scope Rework | Minor drafting revision hours
WBS 1.2 Procurement | +$0.60M | Material Inflation | High-grade tubular steel price surge
WBS 1.3.1 Verdal Yard Fabrication | +$0.20M | Yard Overtime | Welder shift overtime
WBS 1.3.2 Egersund Mast Assembly | +$2.40M | Primary Rework Driver | Pipe fitting misalignment & 24/7 NDT welding
WBS 1.4.1 Heavy Lift Vessel Mobilization | +$1.30M | Marine Standby | Autumn sea-state vessel standby daily rates
WBS 1.4.2 Topside Mating | +$0.10M | Offshore Fit | Offshore trial fitting hours
WBS 1.5 Commissioning & Hook-up | +$0.20M | System Test | Pre-commissioning loops
Time Delay Overhead Spread (SPIt) | +$3.81M | Schedule Overhead | Extending execution past Dec 31 spreads PMO & site overhead
Final Outturn Forecast ($EAC) | $35.41M | Total EAC | Total Outturn Deficit: +$8.91M VAC (-33.6%)

## Slide 5
4. Performance Measurement Baseline (S-Curves) & Variances
Direct Variance Metrics & Time Slippage Analysis at Status Date (Aug 31, 2026)
COST VARIANCE (CV = EV - AC)
-$5,900,000
-33.6% Cost Overrun
SCHEDULE VARIANCE (SV = EV - PV)
-$2,960,000
-14.4% Value Delay
EARNED SCHEDULE (ES)
7.40 Months
Actual Time Elapsed: 8.0M
TIME VARIANCE (SVT)
-18.2 Days
Behind Baseline Plan
Performance Metric | Formula / Standard | Current Value | Threshold Status | Operational Meaning
Planned Value (PV) | Baseline Schedule S-Curve | $20,500,000 | Baseline Target | 77.36% of work scope scheduled
Earned Value (EV) | Physical % Complete × BAC | $17,540,000 | In Progress | 66.19% of work scope accomplished
Actual Spend (AC) | Cumulative General Ledger | $23,440,000 | 🚨 Exceeds EV | Actual funds disbursed
Cost Performance Index (CPI) | EV / AC | 0.7483 | 🚨 Red (< 0.90) | $0.75 earned value generated for every $1.00 spent
Schedule Index (SPI) | EV / PV | 0.8556 | 🟡 Amber (< 0.95) | Scope earned velocity lags baseline schedule
Critical Ratio (CR) | CPI × SPI | 0.6402 | 🚨 Red (< 0.90) | Overall combined project health index
TCPI (Target BAC) | (BAC - EV) / (BAC - AC) | 6.07 | 🚨 Unviable (> 1.10) | Impossible cost efficiency required to hit $26.50M BAC

## Slide 6
5. Executive Variance Explanations & Corrective Actions
Root Cause Analysis & Accountable CAM Response Actions
Variance Indicator | Status Metric | Root Cause Explanation | Actionable Next Steps | Owner
Cost Variance (CV) | -$5,900,000 (CPI = 0.75) | Structural fitting rework & premium overtime at Verdal and Egersund yards. | Enforce Design Change Freeze on WBS 1.3. Convert open T&M subcontracts to fixed unit-rate capped milestones. | O. Eriksen
Outturn Deficit (VAC) | -$8,913,604 (EAC: $35.41M) | Linear extrapolation of poor cost efficiency (CPI=0.75) yields 33.6% overrun. | Submit formal EAC re-baseline proposal. Request $3.50M drawdown from Management Reserve. | Frank Ellingsen
TCPI Target Efficiency | 6.07 (BAC) (Unviable) | Original BAC ceiling requires impossible 607% cost efficiency for remaining work. | Formally transition target to TCPI_EAC = 1.00 based on approved $35.41M EAC. | Frank Ellingsen
Schedule Delay (SV) | -$2,960,000 (+31 Days) | Tubular steel procurement delays cascaded to Verdal and Egersund yards. | Fast-track Egersund rigging with parallel work-fronts. Negotiate 10-day vessel window extension. | M. Berg / K. Solberg
WBS 1.3.2 Mast Assembly | -$2,330,000 (CPI = 0.57) | Egersund rigging yard productivity bottleneck and excessive NDT rework. | Deploy resident Project Controller to Egersund. Audit daily timecards & weld gates. | O. Eriksen

## Slide 7
6. CFO Outturn Forecast & Control Account Financials
Control Account Level EAC Outturns, Cost Variances & Remaining ETC Liquidity
WBS Code | Control Account | BAC Budget | Earned (EV) | Actual (AC) | Cost Var (CV) | CPI | Outturn EAC
1.1.1 | Structural Steel Detail Engineering | $1,200,000 | $1,200,000 | $1,290,000 | -$90,000 | 0.93 | $1,290,000
1.2.1 | High-Grade Tubular Steel Procurement | $3,500,000 | $3,500,000 | $3,770,000 | -$270,000 | 0.93 | $3,770,000
1.3.1 | Yard Sub-Structure Fabrication (Verdal) | $4,000,000 | $3,600,000 | $4,450,000 | -$850,000 | 0.81 | $4,944,000
1.3.2 | Derrick Tower Mast Assembly (Egersund) | $4,800,000 | $3,120,000 | $5,450,000 | -$2,330,000 | 0.57 | $8,385,000

## Slide 8
7. Offshore EPC Gantt Schedule & Critical Path Logic
10 Major Tasks, Predecessor Links, Critical Path (8 Tasks) & Key Milestones
Task ID | WBS | Task Deliverable / Milestone Name | Predecessor | % Complete | Forecast Window | Critical Path
T101 | 1.1.1 | Structural Steel Detail Engineering | - | 100% | Jan 05 - Mar 15 | Yes
M1 | 1.1.0 | ◆ Milestone: Engineering AFC Gate Review | T101 (FS) | 100% | Achieved Mar 15 | Achieved
T102 | 1.1.2 | Piping & Drilling Package Design | T101 (FS) | 100% | Feb 01 - Apr 15 | No
T103 | 1.2.1 | High-Grade Tubular Steel Procurement | T101 (+5D) | 100% | Mar 15 - May 31 | Yes (+31D)
T104 | 1.2.2 | Mud Pumps & Top Drive Equipment | T102 (FS) | 85% | Apr 01 - Jul 31 | No
T105 | 1.3.1 | Yard Sub-Structure Fabrication (Verdal) | T103 (FS) | 90% | Jun 01 - Aug 31 | Yes
M3 | 1.3.0 | ◆ Milestone: Verdal Sub-Structure Handover | T105 (FS) | 90% | Aug 31 | Active
T106 | 1.3.2 | Derrick Tower Mast Assembly (Egersund) | T105 (FS) | 65% | Jul 01 - Sep 30 | Yes (-30D Float)
M4 | 1.3.3 | ◆ Milestone: Derrick Mast Ready for Heavy Lift | T106 (FS) | 65% | Sep 30 Target | Critical Gate
T107 | 1.4.1 | Heavy Lift Vessel Mobilization (Heerema) | T106 (FS) | 30% | Sep 15 - Oct 15 | Yes

## Slide 9
8. EPC Executive Risk Matrix & Mitigation Register
5x5 Quantitative Probability vs. Impact Heatmap & Primary Risk Exposures
Risk ID | Risk Event Description | WBS | Owner | Exposure ($) | Mitigation Strategy
R01 (Score 20) | Egersund Mast Assembly Dimensional Out-of-Tolerance | 1.3.2 | O. Eriksen | $2,400,000 | 24/7 NDT welding specialists; fixed-fee labor cap.
R02 (Score 16) | Heavy Lift Crane Vessel Weather Standby Rates | 1.4.1 | K. Solberg | $1,800,000 | Flexible weather window with Heerema; monitor 7-day wave height.
R03 (Score 12) | Subsea Tubular Steel Mill Delivery Lags | 1.2.1 | M. Berg | $1,200,000 | Dual-source steel from European backup mills; hot-shot freight.
R04 (Score 9) | Topside Lifting & Mating Mechanical Interference | 1.4.2 | T. Nygård | $600,000 | Perform 3D laser scan trial fit prior to offshore mobilization.
R05 (Score 6) | Structural Engineering AFC Interface Errors | 1.1.1 | H. Lindqvist | $300,000 | Enforce 100% 3D CAD clash detection & DNV class verification.

## Slide 10
9. Vertical Swimlane WBS Breakdown by Category
Control Account Summary per Discipline ($26.50M BAC → $35.41M Outturn EAC)
WBS Category | Baseline BAC | Outturn EAC | Status % | Key Control Deliverables
1.1 Engineering | $3.20M | $3.50M | 100% Complete | 1.1.1 Structural Detail ($1.8M), 1.1.2 Piping ($1.4M)
1.2 Procurement | $8.50M | $9.10M | 92.5% Complete | 1.2.1 Tubular Steel ($5.0M), 1.2.2 Drilling Pumps ($3.5M)
1.3 Yard Fabrication | $9.80M | $12.40M | 77.5% In Progress | 1.3.1 Verdal ($5.0M), 1.3.2 Egersund Mast Rework ($4.8M)
1.4 Offshore Installation | $5.00M | $6.40M | 15% In Progress | 1.4.1 Heavy Lift ($3.2M), 1.4.2 Topside Mating ($1.8M)
1.5 Commissioning | $1.80M | $2.00M | 0% Unstarted | 1.5.1 Hook-up & NDT ($1.0M), 1.5.2 Pre-Comm ($0.8M)