## Calculate TCPI
Activity: EVM Assessing Performance
Compare and review your work in steps 2 to 6 using the calculations provided in this worksheet.
Step 2: Determine the TCPI formula best suited to the scenario.
Mala needs to complete the rest of her work within the original time frame. Therefore, to understand the performance level required to complete the remaining 60% of the work in line with the original project plan, you need to calculate TCPI using the Budget at Completion (BAC). The formula for this is TCPI = (BAC − AC) / (BAC − EV).
Step 3: Determine the Budget at Completion (BAC).
To calculate the TCPI, you need to know the Budget at Completion (BAC). In the scenario, Mala plans to spend 14 hours per week working for 5 weeks. The BAC is the total planned effort or total time budgeted in hours.
Formula | BAC = Sum of all planned values
Calculation | Planned hours per week | 14
| Planned number of weeks | 5
| BAC (in hours) | 70
Step 4: Determine the Actual Cost (AC) after 3 weeks.
To calculate the TCPI, you need to know the Actual Cost (AC). In the scenario, AC is the number of hours Mala has actually spent completing her project work up to the end of week 3 (AC).
Formula | AC = Actual Cost incurred for the work performed
Calculation | Given value
| AC (in hours) | 35
Step 5: If the BAC is 70 hours, determine the Earned Value (EV) after 3 weeks.
To calculate the TCPI, you need to know the Earned Value (EV). To find the EV, you need to calculate the percentage of the total planned work that Mala completed at the status date (EV = % complete * BAC).
Formula | EV = % complete * BAC
Calculation | % complete | 40%
| BAC (hours) | 70
| EV (in hours) | 28
Step 6: Calculate the To-Complete Performance Index and interpret the result.
To calculate the TCPI, you need to know the Actual Cost (AC). In the scenario, AC is the number of hours Mala has actually spent completing her project work over 3 weeks (AC). This value is given.
Formula | TCPI = (BAC − EV) / (BAC − AC).
Calculation | BAC − EV | 42
| BAC − AC | 35
| TCPI | 1.2
Threshold comparison (TCPI < 1, TCPI = 1, TCPI > 1) | TCPI > 1