## Calculate forecasting metrics
Step 1: Calculate the Budget at Completion (BAC).
The BAC is original estimate of overall project costs, meaning it is the sum of all the planned values. Thus, the BAC in this scenario is the sum of the planned values for the printing and binding.
Formula | BAC = Sum of all planned values
Calculation | BAC = Total budget planned for printing + total budget planned for binding
| Planned Value for Printing | 250
| Planned Value for Binding | 50
| BAC | 300
Step 2: Calculate the Actual Cost (AC).
The AC is the actual costs incurred for the work completed at the EVM stop point. In this scenario, the actual cost incurred up to the point where the scope changed to include 30 color prints is therefore based on the cost within the original budget.
Formula | AC = Actual costs incurred for completed work
Calculation | AC = Actual cost for printing + actual cost for binding
| Actual cost for printing up to status date (220 black and white pages * $1) | 220
| Actual cost for binding | 50
| AC | 270
Step 3: Calculate the Estimate to Complete (ETC) and Estimate at Completion (EAC).
ETC
The new estimated overall cost (EAC) in this context will be the AC (calculated at $1 per page as per the original estimate and $50 for binding) + the ETC (cost of change in the planned scope). Therefore, to account for the change in scope and cost, you will need to re-estimate the cost of the remaining project work to get the ETC. Instead of $1 per page, the revised cost is $2 per page for 30 pages.
Formula | ETC = Bottom-up ETC
Calculation | ETC = 30 color pages * $2 (cost estimate for additional color pages)
| ETC | 60
EAC
Because ETC is calculated using a bottom-up approach, the first method for calculating EAC is best suited.
Formula | EAC = AC + Bottom-up ETC
Calculation | AC | 270
| Bottom-up ETC | 60
| EAC | 330