## PV_Baseline
Item_ID | WBS_Code | Task_Name | TBC | Month_1 | Month_2 | Month_3 | Month_4 | Month_5 | Month_6
T101 | 1.1.1 | Systems Engineering | 120000 | 40000 | 50000 | 30000 | 0 | 0 | 0
T102 | 1.1.2 | Procurement | 300000 | 100000 | 150000 | 50000 | 0 | 0 | 0
T103 | 1.2.1 | Site Excavation | 180000 | 0 | 20000 | 80000 | 60000 | 20000 | 0
T104 | 1.2.2 | Foundation Concrete | 240000 | 0 | 0 | 40000 | 120000 | 80000 | 0
T105 | 1.3.1 | Structural Assembly | 360000 | 0 | 0 | 0 | 60000 | 200000 | 100000
Total |  | Total Baseline Budget

## Progress_EV
Item_ID | WBS_Code | Task_Name | TBC | Month_1_% | Month_2_% | Month_3_% | Month_4_% | Month_5_% | Month_6_%
T101 | 1.1.1 | Systems Engineering | 120000 | 33.33% | 75% | 100% | 100% | 100% | 100%
T102 | 1.1.2 | Procurement | 300000 | 10% | 50% | 80% | 80% | 90% | 100%
T103 | 1.2.1 | Site Excavation | 180000 | 0% | 11.11% | 55.56% | 88.89% | 100% | 100%
T104 | 1.2.2 | Foundation Concrete | 240000 | 0% | 0% | 10% | 40% | 80% | 100%
T105 | 1.3.1 | Structural Assembly | 360000 | 0% | 0% | 0% | 15% | 60% | 90%

## Actual_Costs
Item_ID | WBS_Code | Task_Name | TBC | Month_1_AC | Month_2_AC | Month_3_AC | Month_4_AC | Month_5_AC | Month_6_AC
T101 | 1.1.1 | Systems Engineering | 120000 | 42000 | 51000 | 32000 | 0 | 0 | 0
T102 | 1.1.2 | Procurement | 300000 | 95000 | 160000 | 55000 | 5000 | 12000 | 28000
T103 | 1.2.1 | Site Excavation | 180000 | 0 | 22000 | 85000 | 45000 | 21000 | 0
T104 | 1.2.2 | Foundation Concrete | 240000 | 0 | 0 | 38000 | 92000 | 84000 | 41000
T105 | 1.3.1 | Structural Assembly | 360000 | 0 | 0 | 0 | 55000 | 185000 | 96000
Total |  | Total Actual Costs

## Dim_WBS
Task_ID | WBS_Code | WBS_Level_1 | WBS_Level_2 | Task_Name | CAM | TBC
T101 | 1.1.1 | 1.0 Engineering | 1.1 Systems | Systems Engineering | L. Hansen | 120000
T102 | 1.1.2 | 1.0 Engineering | 1.1 Systems | Procurement | A. Olsen | 300000
T103 | 1.2.1 | 1.0 Construction | 1.2 Civil Works | Site Excavation | E. Johansen | 180000
T104 | 1.2.2 | 1.0 Construction | 1.2 Civil Works | Foundation Concrete | E. Johansen | 240000
T105 | 1.3.1 | 1.0 Construction | 1.3 Structural | Structural Assembly | K. Andersen | 360000

## Bastick_S_Curve_Model
Liam Bastick Parametric S-Curve Model
Parameter Name | Value
Initial_Percentage_Completed | 0%
Target_Percentage | 100%
Exp_Factor | 2.5
Exp_Growth_Start_Month_No | 1
Exp_Duration_in_Months | 6
Total_Budget_Cost (BAC) | 1200000
Metric / Month | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Month Index (t) | 1 | 2 | 3 | 4 | 5 | 6
Cumulative % Complete (S-Curve)
Cumulative Planned Value ($)
Incremental Planned Value ($)

## Key_Milestones
KEY MILESTONES
Offshore EPC Platform Drill Tower Project — Status Date: Aug 31, 2026
Milestone_ID | Milestone_Name | Target_Date | Baseline_Date | Status | RAG | WBS_Code
M1 | Engineering AFC Gate Review | 2026-03-15 | 2026-03-15 | Achieved | Green | 1.1
M2 | Tubular Steel Material Delivery | 2026-05-31 | 2026-05-31 | Achieved | Green | 1.2
M3 | Verdal Sub-Structure Handover | 2026-08-31 | 2026-08-31 | Active | Green | 1.3.1
M4 | Derrick Mast Ready for Lift | 2026-09-30 | 2026-08-31 | Critical Rework | Red | 1.3.2
M5 | Offshore Topside Mating Complete | 2026-11-15 | 2026-10-31 | Critical Delay | Red | 1.4.2
M6 | Final Commercial COD Handover | 2027-01-31 | 2026-12-31 | Forecast COD | Red | 1.5

## Risk_Register
RISK REGISTER
Offshore EPC Platform Drill Tower Project — Status Date: Aug 31, 2026
Risk_ID | Risk_Title | Category | Probability | Impact | Risk_Score | RAG_Level | Financial_Exposure | Expected_Monetary_Value | Mitigation_Strategy | CAM_Owner
R01 | Egersund Derrick Mast Welding Tolerance Rework | Fabrication | 5 | 5 | 25 | Critical | 2400000 | 2400000 | Capped yard labor hours under fixed-fee contract & 24/7 NDT supervision | Lars Hansen
R02 | North Sea Weather Standby Delay during Mating | Marine | 4 | 4 | 16 | High | 1800000 | 720000 | Secured 14-day flexible mobilization window with Heerema Sleipnir | Erik Solberg
R03 | Subsea Tubular Steel Market Price Surcharges | Procurement | 3 | 3 | 9 | Medium | 600000 | 180000 | Locked bulk steel purchasing under long-term supplier framework | Ingrid Berg
R04 | DNV Class Structural Redesign Review | Engineering | 2 | 3 | 6 | Medium | 300000 | 60000 | Embedded DNV structural lead directly inside project engineering team | Geir Nilsen
R05 | Offshore Hook-up Commissioning Crew Bottleneck | Commissioning | 2 | 2 | 4 | Low | 200000 | 40000 | Pre-commissioned skid packages onshore in Verdal yard | Bjørn Lie

## Waterfall_Bridge
WATERFALL BRIDGE
Offshore EPC Platform Drill Tower Project — Status Date: Aug 31, 2026
Step_ID | Component_Name | Type | Incremental_Cost | Cumulative_Cost | Pct_Share | Description
0 | Original Baseline Budget (BAC) | Baseline | 26500000 | 26500000 | 0 | Approved EPC baseline contract budget ceiling
1 | WBS 1.1 Detail Structural Engineering | Variance | 300000 | 26800000 | 3.4 | Redesign of connection plates & third-party DNV class review
2 | WBS 1.2 Procurement & Tubular Steel | Variance | 600000 | 27400000 | 6.7 | Subsea tubular steel price inflation & mud pump freight surcharge
3 | WBS 1.3.1 Verdal Sub-Structure Yard | Variance | 200000 | 27600000 | 2.2 | Minor yard overtime for weld inspection
4 | WBS 1.3.2 Egersund Derrick Mast Rework | Variance | 2400000 | 30000000 | 26.9 | PRIMARY YARD REWORK DRIVER: Pipe out-of-tolerance & 24/7 NDT welding
5 | WBS 1.4.1 Heavy Lift Vessel Standby | Variance | 1300000 | 31300000 | 14.6 | North Sea autumn weather standby rates (Heerema Sleipnir)
6 | WBS 1.4.2 Topside Lifting & Mating | Variance | 100000 | 31400000 | 1.1 | Pre-lift trial fitting and alignment fixtures
7 | WBS 1.5 Hook-up & Commissioning | Variance | 200000 | 31600000 | 2.2 | Extended offshore commissioning specialist crew
8 | Time Delay Overhead Spread (SPI_t) | Variance | 3813604 | 35413604 | 42.8 | TIME DELAY SPREAD: +31-day delay spreading PMO & site overhead
9 | Final Outturn Forecast (EAC) | Outturn | 35413604 | 35413604 | 100 | Final predicted cost outcome at project completion

## Cash_Burn_Rate
CASH BURN RATE
Offshore EPC Platform Drill Tower Project — Status Date: Aug 31, 2026
Period | Monthly_PV | Monthly_EV | Monthly_AC | Cum_AC | Remaining_BAC | Runway_Status
M1 (Jan 26) | 300000 | 300000 | 320000 | 320000 | 26180000 | Baseline Runway
M2 (Feb 26) | 900000 | 840000 | 950000 | 1270000 | 25230000 | Baseline Runway
M3 (Mar 26) | 2700000 | 2260000 | 2900000 | 4170000 | 22330000 | Baseline Runway
M4 (Apr 26) | 3800000 | 3520000 | 4050000 | 8220000 | 18280000 | Baseline Runway
M5 (May 26) | 3000000 | 2900000 | 3220000 | 11440000 | 15060000 | Baseline Runway
M6 (Jun 26) | 4000000 | 2750000 | 4450000 | 15890000 | 10610000 | Peak Yard Spend Phase
M7 (Jul 26) | 3000000 | 2620000 | 3850000 | 19740000 | 6760000 | Peak Yard Spend Phase
M8 (Aug 26 - Now) | 2800000 | 2350000 | 3700000 | 23440000 | 3060000 | Critical Runway ($3.06M Left)
M9 (Sep 26 - Burn) | 2500000 | 2100000 | 3200000 | 26640000 | -140000 | 100% BUDGET BURN OUT!
M10 (Oct 26) | 1500000 | 2200000 | 3300000 | 29940000 | -3440000 | Overrun Financing Phase
M11 (Nov 26) | 1000000 | 2000000 | 2500000 | 32440000 | -5940000 | Overrun Financing Phase
M12 (Dec 26) | 1000000 | 1800000 | 1800000 | 34240000 | -7740000 | Overrun Financing Phase
M13 (Jan 27 - COD) | 0 | 860000 | 1173604 | 35413604 | -8913604 | Final COD (+8.91M Overrun)

## Financial_Ratios
FINANCIAL RATIOS
Offshore EPC Platform Drill Tower Project — Status Date: Aug 31, 2026
Metric | Value | Numeric_Value | Unit | Evaluation
Net Present Value (NPV @ 10% WACC) | +$14,899,563 | 14899563 | USD | Strong Positive Net Present Value
Internal Rate of Return (IRR) | 18.86% | 0.1886 | % | Outperforms 10.0% Hurdle Rate by +886 bps
Simple Payback Period | 4.43 Years | 4.43 | Years | 53.1 Months (May 2031)
Profitability Index (PI) | 1.42 | 1.42 | Ratio | Generates $1.42 PV per $1.00 spent
Total Simple ROI | 134.37% | 1.3437 | % | High 10-year cumulative commercial return
Annualized ROI (CAGR) | 8.89% | 0.0889 | %/Year | Compounded annual growth rate
Gross Future Value Year 10 (FV) | $130,499,397 | 130499397 | USD | Nominal cash generated across 10 years
Net Future Value (NFV) | +$38,645,628 | 38645628 | USD | Net future value after CAPEX outturn

## Monte_Carlo_P90
MONTE CARLO P90
Offshore EPC Platform Drill Tower Project — Status Date: Aug 31, 2026
Percentile | Confidence_Level | Outturn_Cost_EAC | Cost_Overrun_VAC | Contingency_Reserve | Duration_Days | Completion_Date | Schedule_Delay_Days
P10 | 10% Optimistic | 32444302 | -5944302 | 0 | 408.1 | 2027-02-13 | 43.1
P50 | 50% Median | 34060783 | -7560783 | 0 | 422.3 | 2027-02-27 | 57.3
P80 | 80% Standard | 35195026 | -8695026 | 0 | 432.3 | 2027-03-09 | 67.3
P90 | 90% High Confidence | 35815202 | -9315202 | 401598 | 437.5 | 2027-03-14 | 72.5
P95 | 95% Extreme Risk | 36272986 | -9772986 | 859382 | 441.6 | 2027-03-18 | 76.6