## Executive Briefing
North Sea Platform Drill Tower Construction
Executive Steering Committee Monthly Briefing ¦ Status Date: Aug 31, 2026
🚨 OVERALL HEALTH: CRITICAL COST OVERRUN & SCHEDULE SLIPPAGE (RED) ¦ BAC Budget Burn Out: Month 9 (Sep 2026)
1. Key EVM Performance Metrics
Metric Name | Acronym | Current Value | Baseline Target | Variance ($ / %) | Performance Index | Status Health | Context & Threshold Notes
Approved Baseline Budget | BAC | 26500000 | 26500000 | 0 | 1 | Approved Target | Original baseline budget ceiling
Earned Work Complete | EV | 17540000 | 26500000 |  |  | 66.2% Complete | Earned physical work accomplished
Planned Baseline Target | PV | 20500000 | 26500000 |  |  | 77.4% Scheduled | Scheduled baseline progress to date
Cumulative Actual Spend | AC | 23440000 | 26500000 |  |  | Severe Overrun | Actual ledger expenditure ($5.90M > EV)
Cost Variance | CV |  | 0 |  |  | 🚨 CRITICAL | Overrun of -$5.90M (CPI = 0.748)
Schedule Variance | SV |  | 0 |  |  | 🟡 DELAYED | Value delay of -$2.96M (SPI = 0.856)
Earned Schedule Velocity | SPIt | 0.925 | 1 | -18.2 | 0.925 | 🟡 -18 Days | Time-based schedule velocity (ES 7.40M)
To-Complete Index (BAC) | TCPI_BAC |  | 1 | 5.07 | 6.07 | 🚨 UNVIABLE | Requires impossible 607% efficiency
2. Outturn Predictions & P90 Risk Reserve
Scenario | EAC Outturn ($) | Variance at Completion (VAC) | Completion Date | Schedule Slip | Risk Reserve Required ($)
Deterministic Base EAC | 35413604 |  | 2027-01-31 | +31 Days | 0
Monte Carlo P50 Forecast | 34060783 |  | 2027-02-27 | +57 Days | 0
Monte Carlo P90 Risk Ceiling | 35815202 |  | 2027-03-14 | +72 Days

## Runway & Cash Burn
Monthly Cash Burn Speed & Budget Depletion Forecast
Exact BAC Budget Exhaustion Point: Month 9 (September 2026)
AVG MONTHLY CASH BURN |  | REMAINING BASELINE CAPITAL |  | BUDGET BURN OUT MONTH |  | REQUIRED OVERRUN FINANCING
2930000 |  | 3060000 |  | Month 9 (Sep 2026) |  | 8913604
Baseline Plan: $2.56M/Month (+14.5% faster) |  | $23.44M spent of $26.50M BAC budget |  | 100% of $BAC budget ceiling exhausted |  | Needs approval before Sep 15, 2026
Monthly Cash Burn Speed ($PV, $EV, $AC) & Budget Exhaustion Schedule
Month # | Calendar Month | Planned Monthly ($PV) | Earned Monthly ($EV) | Actual Monthly ($AC) | Cumulative Spend ($AC) | Remaining Capital ($BAC - AC) | Runway Status & Depletion Note
1 | Month 1 (Jan 2026) | 300000 | 300000 | 320000 |  |  | Detail steel engineering ramp-up
2 | Month 2 (Feb 2026) | 900000 | 840000 | 950000 |  |  | Engineering completed on baseline
3 | Month 3 (Mar 2026) | 2700000 | 2260000 | 2900000 |  |  | Procurement placement delays
4 | Month 4 (Apr 2026) | 3800000 | 3520000 | 4050000 |  |  | Verdal yard sub-structure start
5 | Month 5 (May 2026) | 3000000 | 2900000 | 3220000 |  |  | Sub-structure assembly
6 | Month 6 (Jun 2026) | 4000000 | 2750000 | 4450000 |  |  | Egersund mast fitting misalignment rework
7 | Month 7 (Jul 2026) | 3000000 | 2620000 | 3850000 |  |  | Double-shift NDT welding labor
8 | Month 8 (Aug 2026) | 2800000 | 2350000 | 3700000 |  |  | Status Date: $23.44M cumulative actual spend
9 | Month 9 (Sep 2026) | 2500000 | 2100000 | 3200000 |  |  | 💥 100% BAC Budget Exhausted (Burn Out)
10 | Month 10 (Oct 2026) | 1500000 | 2200000 | 3300000 |  |  | Overrun Financing Phase (Heerema Marine)

## Cost Variance Waterfall
Cost Variance Waterfall Bridge ($BAC → EAC Outturn Breakdown)
Step-by-Step Cost Variance Drivers from Baseline to Outturn Forecast
Step-by-Step Variance Bridge per WBS Control Account
Step # | WBS Control Account / Driver | Step Variance ($) | Cumulative Total ($) | Variance Category | Root Cause Driver Explanation
0 | Approved Baseline Budget ($BAC) | 26500000 |  | Baseline Target | Approved original contract baseline budget
1 | WBS 1.1 Detail Engineering | 300000 |  | Scope Rework | Minor drafting revision hours
2 | WBS 1.2 Procurement | 600000 |  | Material Inflation | High-grade tubular steel market price surge
3 | WBS 1.3.1 Verdal Yard Fabrication | 200000 |  | Yard Overtime | Welder shift overtime
4 | WBS 1.3.2 Egersund Mast Assembly | 2400000 |  | Primary Rework Driver | Pipe fitting misalignment & 24/7 NDT welding
5 | WBS 1.4.1 Heavy Lift Vessel Mobilization | 1300000 |  | Marine Standby | Autumn sea-state vessel standby daily rates
6 | WBS 1.4.2 Topside Mating | 100000 |  | Offshore Fit | Offshore trial fitting hours
7 | WBS 1.5 Commissioning & Hook-up | 200000 |  | System Test | Pre-commissioning loops
8 | Time Delay Overhead Spread (SPIt) | 3813604 |  | Schedule Overhead | Extending execution past Dec 31 spreads PMO & site overhead
9 | Final Outturn Forecast ($EAC) | 0 |  | Total EAC Outturn | Total Outturn Deficit: +$8.91M VAC (-33.6%)

## EVM & S-Curve Performance
Performance Measurement Baseline (S-Curves) & Cumulative EVM
Direct Endpoint Metrics, Cost Variance & Time Slippage Analysis
Monthly Cumulative Performance Measurement Baseline (PMB S-Curve)
Month # | Month Name | Planned Value ($PV) | Earned Value ($EV) | Actual Cost ($AC) | Cost Variance ($CV) | Schedule Variance ($SV) | CPI Index | SPI Index
1 | Jan 2026 | 300000 | 300000 | 320000
2 | Feb 2026 | 1200000 | 1140000 | 1270000
3 | Mar 2026 | 3900000 | 3400000 | 4170000
4 | Apr 2026 | 7700000 | 6920000 | 8220000
5 | May 2026 | 10700000 | 9820000 | 11440000
6 | Jun 2026 | 14700000 | 12570000 | 15890000
7 | Jul 2026 | 17700000 | 15190000 | 19740000
8 | Aug 2026 (Status) | 20500000 | 17540000 | 23440000

## CFO Financials
CFO Control Account Financials & Outturn Forecast
Control Account Level EAC Outturns, Cost Variances & Remaining ETC Liquidity
Control Account Financial Performance & Liquidity Target
WBS Code | Control Account Name | Baseline Budget ($BAC) | Earned Value ($EV) | Actual Cost ($AC) | Cost Variance ($CV) | CPI Index | Outturn Forecast ($EAC) | Outturn Deficit ($VAC) | Remaining Liquidity ($ETC)
1.1.1 | Structural Steel Detail Engineering | 1200000 | 1200000 | 1290000 |  |  | 1290000
1.2.1 | High-Grade Tubular Steel Procurement | 3500000 | 3500000 | 3770000 |  |  | 3770000
1.3.1 | Yard Sub-Structure Fabrication (Verdal) | 4000000 | 3600000 | 4450000 |  |  | 4944000
1.3.2 | Derrick Tower Mast Assembly (Egersund) | 4800000 | 3120000 | 5450000 |  |  | 8385000

## Gantt & Critical Path
Offshore EPC Gantt Schedule & Critical Path Logic
10 Major Schedule Tasks, Predecessor Logic, Critical Path (8 Tasks) & Key Milestones
EPC Schedule Master Activity & Critical Path Register
Task ID | WBS Code | Task Deliverable / Milestone Name | Predecessor | Type | Total Float | % Complete | Baseline Window | Forecast Window | Critical Path Flag
T101 | 1.1.1 | Structural Steel Detail Engineering | - | - | 0 Days | 100% | Jan 05 - Feb 28 | Jan 05 - Mar 15 | Yes
M1 | 1.1.0 | ◆ Milestone: Engineering AFC Gate Review | T101 | FS | 0 Days | 100% | Feb 28 | Achieved Mar 15 | Achieved Gate
T102 | 1.1.2 | Piping & Drilling Package Design | T101 | FS | +14 Days | 100% | Feb 01 - Mar 31 | Feb 01 - Apr 15 | No
T103 | 1.2.1 | High-Grade Tubular Steel Procurement | T101 (+5D) | FS | 0 Days | 100% | Mar 01 - Apr 30 | Mar 15 - May 31 | Yes (+31D Delay)
T104 | 1.2.2 | Mud Pumps & Top Drive Equipment | T102 | FS | +15 Days | 85% | Mar 15 - Jun 30 | Apr 01 - Jul 31 | No
T105 | 1.3.1 | Yard Sub-Structure Fabrication (Verdal) | T103 | FS | 0 Days | 90% | May 01 - Jul 31 | Jun 01 - Aug 31 | Yes
M3 | 1.3.0 | ◆ Milestone: Verdal Sub-Structure Handover | T105 | FS | 0 Days | 90% | Jul 31 | Aug 31 Handover | Active Gate
T106 | 1.3.2 | Derrick Tower Mast Assembly (Egersund) | T105 | FS | 0 Days | 65% | Jun 01 - Aug 31 | Jul 01 - Sep 30 | Yes (-30D Float)
M4 | 1.3.3 | ◆ Milestone: Derrick Mast Ready for Heavy Lift | T106 | FS | 0 Days | 65% | Aug 31 | Sep 30 Target | Critical Gate
T107 | 1.4.1 | Heavy Lift Vessel Mobilization (Heerema) | T106 | FS | 0 Days | 30% | Aug 15 - Sep 15 | Sep 15 - Oct 15 | Yes