## Slide 1
OFFSHORE EPC PLATFORM DRILL TOWER PROJECT
Executive Steering Committee Status Briefing & Commercial Appraisal
Status Date: August 31, 2026 (Month 8 / Status Week 36) Author: Frank Ellingsen, Lead Project Controller

## Slide 2
PROJECT HEALTH & CORE EVM DASHBOARD
Month 8 (Aug 2026) Earned Value Performance Metrics
Metric | Description | Value | Status
BAC | Baseline Contract Budget | $26,500,000 | Approved
PV | Planned Value Baseline | $20,500,000 | 77.4% Planned
EV | Earned Value Complete | $17,540,000 | 66.2% Complete
AC | Cumulative Actual Cost | $23,440,000 | CRITICAL OVERRUN
CPI | Cost Efficiency Index | 0.7483 | Red ($0.75 / $1.00)
SPI_t | Earned Schedule Velocity | 0.9250 | Amber (-18.2 Days)
🚨 EXECUTIVE ALERT
• Baseline Budget Depletion: Month 9 (Sep 2026) • Required Financing Line: +$8,913,604 • Outturn Cost EAC: $35.41M (+33.6% Overrun) • Outturn Completion: Jan 31, 2027 (+31 Days Delay) • Primary Driver: Egersund Mast Rework ($2.40M) & Delay Overhead ($3.81M)

## Slide 3
COMMERCIAL CAPITAL BUDGETING & APPRAISAL RATIOS
Project Investment Return Metrics (10.0% WACC Hurdle Rate)
Commercial Metric | Calculated Value | Benchmark / Hurdle | Commercial Evaluation
Net Present Value (NPV @ 10%) | +$14,899,563 | $0.00 Hurdle | Strong Positive Net Capital Value
Internal Rate of Return (IRR) | 18.86% | 10.0% Hurdle Rate | Outperforms Hurdle Target by +886 bps
Simple Payback Period | 4.43 Years | < 5.0 Years Target | 53.1 Months (May 2031) Payback
Profitability Index (PI) | 1.42 | > 1.0 Ratio | Generates $1.42 PV per $1.00 spent
Total Simple ROI | 134.37% | 100.0% Base | High 10-Year Cumulative Return
Annualized ROI (CAGR) | 8.89%/Year | 5.0% Risk-Free | Compounded Annual Growth Rate
Gross Future Value (FV Yr 10) | $130,499,397 | CAPEX Base | Total Operating Inflow
Net Future Value (NFV) | +$38,645,628 | CAPEX Outturn | Net Future Cash Surplus

## Slide 4
MONTE CARLO RISK SIMULATION (10,000 ITERATIONS)
Statistical Outturn Percentiles & Contingency Reserves
Percentile | Confidence Level | Outturn EAC | Cost Overrun | Completion Date | Schedule Delay
P10 | 10% Optimistic | $32,444,302 | -$5,944,302 | Feb 13, 2027 | +43.1 Days
P50 | 50% Median | $34,060,783 | -$7,560,783 | Feb 27, 2027 | +57.3 Days
P80 | 80% Standard Budget | $35,195,026 | -$8,695,026 | Mar 09, 2027 | +67.3 Days
P90 | 90% High Confidence | $35,815,202 | -$9,315,202 | Mar 14, 2027 | +72.5 Days
P95 | 95% Extreme Risk | $36,272,986 | -$9,772,986 | Mar 18, 2027 | +76.6 Days
P90 HIGH-CONFIDENCE TARGET: $35,815,202 Outturn Cost | March 14, 2027 Completion Date Contingency Reserve Needed: +$401,598 above base EAC to achieve 90% financial confidence.

## Slide 5
5X5 EXECUTIVE RISK MATRIX & ACTIVE REGISTER
Top Project Risks R01 - R05 with Financial Exposure
Risk ID | Risk Title | Severity | Financial Exposure | EMV Value | Accountable CAM
R01 | Egersund Derrick Mast Yard Rework | 5x5 Critical | $2,400,000 | $2,400,000 | Lars Hansen
R02 | North Sea Weather Standby Delay | 4x4 High | $1,800,000 | $720,000 | Erik Solberg
R03 | Tubular Steel Price Inflation | 3x3 Medium | $600,000 | $180,000 | Ingrid Berg
R04 | DNV Structural Redesign Review | 2x3 Medium | $300,000 | $60,000 | Geir Nilsen
R05 | Offshore Hook-up Crew Bottleneck | 2x2 Low | $200,000 | $40,000 | Bjørn Lie

## Slide 6
COST VARIANCE WATERFALL BRIDGE ($BAC TO EAC)
Step-by-Step Cost Overrun Progression across Control Accounts
Step | Control Account / Variance Component | Incremental Overrun | Cumulative Cost | % Contribution
0 | Original Baseline Budget (BAC) | $26,500,000 | $26,500,000 | 0.0%
1 | Detail Structural Engineering Revisions | +$300,000 | $26,800,000 | 3.4%
2 | Procurement Steel Price Inflation | +$600,000 | $27,400,000 | 6.7%
3 | Verdal Sub-Structure Fabrication | +$200,000 | $27,600,000 | 2.2%
4 | Egersund Derrick Mast Yard Rework | +$2,400,000 | $30,000,000 | 26.9%
5 | Heavy Lift Vessel Weather Standby | +$1,300,000 | $31,300,000 | 14.6%
6 | Offshore Topside Lifting & Mating | +$100,000 | $31,400,000 | 1.1%
7 | Hook-up & Commissioning Crew | +$200,000 | $31,600,000 | 2.2%
8 | Time Delay Overhead Spread (SPI_t) | +$3,813,604 | $35,413,604 | 42.8%

## Slide 7
STEERING COMMITTEE DECISION MATRIX & ACTION PLAN
Required Executive Approvals & Project Recovery Directives
RECOMMENDED STEERING COMMITTEE ACTIONS:
1. AUTHORIZE +$8.91M OVERRUN FINANCING LINE:
• Executive Board approval required before September 15, 2026 to prevent Month 9 yard shutdown.
2. ENFORCE FIXED-FEE CAP ON EGERSUND YARD BILLING:
• Transition remaining Derrick Mast assembly hours to a fixed-fee cap to halt further cost escalation.
3. COMPRESS OFFSHORE HOOK-UP SCHEDULE:
• Recover 15 calendar days along the critical path to preserve the January 31, 2027 Commercial COD.